# **13th February 2023; 14:00 – 15:00 – Meeting**

|  |  |
| --- | --- |
|  | |
| **Document Intention:** | Meeting information. |
| **Document Authors:** | Alfred Manville |
| **Document Version Date-Stamp:** | 19/02/2023 |
| **Document Version:** | 1 |
| **Document Version History:** | |
| 1. Created document. | |
| **Meeting Itinerary:** | |
| * Discuss progress. | |

**Meeting Results**

* Work out a new roadmap to use for the rest of the design phase.
* Create a better way to work together online.
* Try to keep most of the work from being done by the project manager.

**Roadmap**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ID** | **Due** | **Task Description** | **Assigned** | **Blocked By** | **Start** |
| 1 | 16/02/23 | Finish Use Case Specifications (10) | Mohamed Mudhir, Maudud Ahmed, Huzaifa Pathan |  | 12/02/23 |
| 2 | 17/02/23 | Complete noun-verb-association highlighting and table (Optional: Do class Analysis Diagram) | Alfred Manville, Maudud Ahmed |  | 15/02/23 |
| 3 | 17/02/23 | Complete risk analysis initial to pass on to PM | Karan Sambee, Mohamed Mudhir |  | 14/02/23 |
| 4 | 16/02/23 | Binder Re-organisation | Alfred Manville | 1, 3 | 15/02/23 |
| 5 | 20/02/23 | Complete class associations in design diagram and boundary classes | TBA | 1 | 18/02/23 |
| 6 | 19/02/23 | Complete Use Case list and priorities. | TBA | 1 | 17/02/23 |
| 7 | 26/02/23 | Complete existing system description | TBA |  | 15/02/23 |
| 8 | 26/02/23 | Complete class design diagram | TBA | 5 | 18/02/23 |
| 9 | 22/02/23 | Complete GUIs | Karan Sambee | 5 | 14/02/23 |
| 10 | 26/02/23 | Complete ER diagram | TBA | 8 | 23/02/23 |
| 11 | 01/03/23 | Complete SQL and Schema | TBA | 10 | 26/02/23 |