# **Tasks Log**

|  |  |
| --- | --- |
|  | |
| **Document Intention:** | Contains a chronological list of all tasks and any updates done to the roadmaps they are part of. |
| **Document Authors:** | Alfred Manville |
| **Document Version Date-Stamp:** | 22/04/2023 |
| **Document History (Contents):** | |
| Contents  [**Tasks Log** 1](#_Toc130479150)  [**Ending 12th February 2023 Roadmap – 8th February 2023** 1](#_Toc130479151)  [**Ending 5th March 2023 Roadmap – 14th February 2023** 1](#_Toc130479152)  [**Ending 5th March 2023 Roadmap – 19th February 2023** 2](#_Toc130479153)  [**Ending 5th March 2023 Roadmap – 24th February 2023** 2](#_Toc130479154)  [**Ending 9th April 2023 Roadmap – 13th February 2023** 3](#_Toc130479155)  [**Ending 9th April 2023 Roadmap – 22nd February 2023** 3](#_Toc130479156) | |

# **Ending 12th February 2023 Roadmap – 8th February 2023**

|  |  |  |
| --- | --- | --- |
| **Task** | **Assigned** | **Deadline** |
| Complete use case analysis diagram. | Samina Matin, Syed Hussain | 11/02/2023 |
| Complete use case analysis specifications. | Mohamed Mudhir, Maudud Ahmed, Huzaifa Pathan | 12/02/2023 |
| Complete class analysis diagram. | Alfred Manville, Maudud Ahmed | 13/02/2023 |
| Start GUI designing. | Karan Sambee | TBA – Also requires boundary classes from class design diagram. |

# **Ending 5th March 2023 Roadmap – 14th February 2023**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ID** | **Due** | **Task Description** | **Assigned** | **Blocked By** | **Start** |
| 1 | 16/02/23 | Finish Use Case Specifications (10) | Mohamed Mudhir, Maudud Ahmed, Huzaifa Pathan |  | 12/02/23 |
| 2 | 17/02/23 | Complete class analysis diagram | Alfred Manville, Maudud Ahmed |  | 15/02/23 |
| 3 | 17/02/23 | Complete risk analysis initial to pass on to PM | Karan Sambee, Mohamed Mudhir |  | 14/02/23 |
| 4 | 16/02/23 | Binder Re-organisation | Alfred Manville | 1, 3 | 15/02/23 |
| 5 | 19/02/23 | Complete class associations in design diagram and boundary classes |  | 1 | 18/02/23 |
| 6 | 19/02/23 | Complete Use Case list and priorities. | Alfred Manville | 1 | 17/02/23 |
| 7 | 26/02/23 | Complete existing system description | Alfred Manville |  | 15/02/23 |
| 8 | 26/02/23 | Complete class design diagram |  | 5 | 18/02/23 |
| 9 | 20/02/23 | Complete GUIs | Karan Sambee | 5 | 14/02/23 |
| 10 | 26/02/23 | Complete ER diagram |  | 8 | 23/02/23 |
| 11 | 01/03/23 | Complete SQL and Schema |  | 10 | 26/02/23 |

# **Ending 5th March 2023 Roadmap – 19th February 2023**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ID** | **Due** | **Task Description** | **Assigned** | **Blocked By** | **Start** |
| 1 | 16/02/23 | Finish Use Case Specifications (10) | Mohamed Mudhir, Maudud Ahmed, Huzaifa Pathan |  | 12/02/23 |
| 2 | 17/02/23 | Complete noun-verb-association highlighting and table (Optional: Do class Analysis Diagram) | Alfred Manville, Maudud Ahmed |  | 15/02/23 |
| 3 | 17/02/23 | Complete risk analysis initial to pass on to PM | Karan Sambee, Mohamed Mudhir |  | 14/02/23 |
| 4 | 16/02/23 | Binder Re-organisation | Alfred Manville | 1, 3 | 15/02/23 |
| 5 | 20/02/23 | Complete class associations in design diagram and boundary classes | TBA | 1 | 18/02/23 |
| 6 | 19/02/23 | Complete Use Case list and priorities. | TBA | 1 | 17/02/23 |
| 7 | 26/02/23 | Complete existing system description | TBA |  | 15/02/23 |
| 8 | 26/02/23 | Complete class design diagram | TBA | 5 | 18/02/23 |
| 9 | 22/02/23 | Complete GUIs | Karan Sambee | 5 | 14/02/23 |
| 10 | 26/02/23 | Complete ER diagram | TBA | 8 | 23/02/23 |
| 11 | 01/03/23 | Complete SQL and Schema | TBA | 10 | 26/02/23 |

# **Ending 5th March 2023 Roadmap – 24th February 2023**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ID** | **Due** | **Task Description** | **Assigned** | **Blocked By** | **Start** |
| 1 | 16/02/23 | Finish Use Case Specifications (10) | Mohamed Mudhir, Maudud Ahmed, Huzaifa Pathan |  | 12/02/23 |
| 2 | 17/02/23 | Complete noun-verb-association highlighting and table (Optional: Do class Analysis Diagram) | Alfred Manville, Maudud Ahmed |  | 15/02/23 |
| 3 | 17/02/23 | Complete risk analysis initial to pass on to PM | Karan Sambee, Mohamed Mudhir |  | 14/02/23 |
| 4 | 16/02/23 | Binder Re-organisation | Alfred Manville | 1, 3 | 15/02/23 |
| 5 | 20/02/23 | Complete class associations in design diagram and boundary classes |  | 1 | 18/02/23 |
| 6 | 19/02/23 | Complete Use Case list and priorities. | Alfred Manville | 1 | 17/02/23 |
| 7 | 26/02/23 | Complete existing system description | Alfred Manville |  | 15/02/23 |
| 8 | 26/02/23 | Complete class design diagram | Samina Matin | 5 | 18/02/23 |
| 9 | 22/02/23 | Complete GUIs | Karan Sambee | 5 | 14/02/23 |
| 10 | 26/02/23 | Complete ER diagram | Samina Matin | 8 | 23/02/23 |
| 11 | 01/03/23 | Complete SQL and Schema |  | 10 | 26/02/23 |

# **Ending 9th April 2023 Roadmap – 13th March 2023**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ID** | **Due** | **Task Description** | **Assigned** | **Blocked By** | **Start** |
| 1 | 15/03/2023 | Utils Package | Samina Matin |  | 14/03/2023 |
| 2 | 26/03/2023 | Component Diagram | Alfred Manville |  | 19/03/2023 |
| 3 | 05/04/2023 | Test Plans | Huzaifa Pathan |  | 20/03/2023 |
| 4 | 05/04/2023 | Testing | Samina Matin | 3 | 20/03/2023 |
| 5 | 15/03/2023 | Database Package | Alfred Manville | 13 | 14/03/2023 |
| 6 | 27/03/2023 | Sales Package |  | 5, 8, 9, 13 | 21/03/2023 |
| 7 | 18/03/2023 | Stock Package | Syed Hussain | 5, 13 | 15/03/2023 |
| 8 | 18/03/2023 | Staff Package |  | 1, 5, 13 | 15/03/2023 |
| 9 | 18/03/2023 | Rates Package | Mohamed Mudhir | 5, 13 | 15/03/2023 |
| 10 | 18/03/2023 | Customers Package | Syed Hussain | 1, 5, 13 | 15/03/2023 |
| 11 | 04/04/2023 | Reports Package | Karan Sambee | 6, 7, 13 | 28/03/2023 |
| 12 | 29/03/2023 | GUI Package | Alfred Manville | 13 | 16/03/2023 |
| 13 | 14/03/2023 | Standard Initial Interfaces | Alfred Manville |  | 14/03/2023 |

# **Ending 9th April 2023 Roadmap – 22nd March 2023**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ID** | **Due** | **Task Description** | **Assigned** | **Blocked By** | **Start** |
| 1 | 15/03/2023 | Utils Package | Samina Matin |  | 14/03/2023 |
| 2 | 09/04/2023 | Component Diagram | Alfred Manville |  | 03/04/2023 |
| 3 | 10/04/2023 | Test Plans | Huzaifa Pathan |  | 29/03/2023 |
| 4 | 11/04/2023 | Testing | Samina Matin | 3 | 03/04/2023 |
| 5 | 15/03/2023 | Database Package | Alfred Manville | 13 | 14/03/2023 |
| 6 | 29/03/2023 | Sales Package |  | 5, 8, 9, 13 | 1/04/2023 |
| 7 | 24/03/2023 | Stock Package | Syed Hussain | 5, 13 | 21/03/2023 |
| 8 | 24/03/2023 | Staff Package | Karan Sambee | 1, 5, 13 | 21/03/2023 |
| 9 | 26/03/2023 | Rates Package | Mohamed Mudhir | 5, 13 | 21/03/2023 |
| 10 | 29/03/2023 | Customers Package | Syed Hussain, Karan Sambee | 1, 5, 13 | 25/03/2023 |
| 11 | 04/04/2023 | Reports Package | Karan Sambee | 6, 7, 13 | 28/03/2023 |
| 12 | 02/04/2023 | GUI Package | Alfred Manville | 13 | 24/03/2023 |
| 13 | 14/03/2023 | Standard Initial Interfaces | Alfred Manville |  | 14/03/2023 |
|  |  |  |  |  |  |

# **Ending 9th April 2023 Roadmap – 9th April 2023**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ID** | **Due** | **Task Description** | **Assigned** | **Blocked By** | **Start** |
| 1 | 15/03/2023 | Utils Package | Samina Matin |  | 14/03/2023 |
| 2 | 09/04/2023 | Component Diagram | Alfred Manville |  | 03/04/2023 |
| 3 | 10/04/2023 | Test Plans | Huzaifa Pathan |  | 29/03/2023 |
| 4 | 11/04/2023 | Testing | Samina Matin | 3 | 03/04/2023 |
| 5 | 15/03/2023 | Database Package | Alfred Manville | 13 | 14/03/2023 |
| 6 | 29/03/2023 | Sales Package |  | 5, 8, 9, 13 | 1/04/2023 |
| 7 | 24/03/2023 | Stock Package | Syed Hussain | 5, 13 | 21/03/2023 |
| 8 | 24/03/2023 | Staff Package | Karan Sambee | 1, 5, 13 | 21/03/2023 |
| 9 | 26/03/2023 | Rates Package | Mohamed Mudhir | 5, 13 | 21/03/2023 |
| 10 | 29/03/2023 | Customers Package | Syed Hussain, Karan Sambee | 1, 5, 13 | 25/03/2023 |
| 11 | 04/04/2023 | Reports Package | Karan Sambee | 6, 7, 13 | 28/03/2023 |
| 12 | 02/04/2023 | GUI Package | Alfred Manville | 13 | 24/03/2023 |
| 13 | 14/03/2023 | Standard Initial Interfaces | Alfred Manville |  | 14/03/2023 |